TOOLKIT AFRICA

# Weekly Work Plan

27–31 JULY 2026  |  SMART LECTURER 3D INTEGRATION

# Purpose

Convert the validated Meshy lecturer source into a locally running, animation-ready browser character and close the week with evidence-based visual acceptance.

# Verified starting position

A cohesive textured Meshy 5 lecturer GLB is stored locally and tracked in Git.

The source contains one mesh/material but no armature or facial shape keys.

The existing Three.js controller already defines lighting, head motion, blink and viseme inputs.

The current runtime still serves the older MPFB diagnostic GLB.

The production build passes; the final local review server and Meshy screenshots are pending.

# Daily plan

| Day | Primary work | Required output | Release gate |
| --- | --- | --- | --- |
| Mon 27 | Research, prototype audit, Meshy generation and structural validation. | Tracked source GLB, provenance, topology record and honest integration status. | No final claim from asset acquisition alone. |
| Tue 28 | Prepare non-destructive Blender rig; establish head, neck, jaw and eye controls. | Rigged source blend and neutral/head-turn Blender renders. | No tearing, disconnected geometry or texture damage. |
| Wed 29 | Create blink and minimum speech shape set; connect Rhubarb cue mapping. | Blink plus at least three distinct speech poses with closed-mouth neutral. | Silence closes mouth; expression remains professional. |
| Thu 30 | Optimize/export GLB and integrate with Three.js controller. | Meshy runtime asset with fixed lighting, head movement, voice and recovery paths. | Desktop and mobile frame rate/visual quality acceptable. |
| Fri 31 | Run Brave matrix, build/security checks and human review preparation. | Final screenshots, evidence JSON, test record, milestone close or explicit hold. | Do not close milestone with seams, silent speech or static head. |

# Acceptance criteria

| Area | Completion test | Control |
| --- | --- | --- |
| Face | Intact neutral face at front and turned views. | No black seams, floating helpers or lighting flicker. |
| Head motion | Autonomous and pointer-responsive yaw/pitch. | Natural limits; shoulders and torso remain stable. |
| Speech | Audible local neural voice and timed mouth shapes. | Text remains canonical; silence and pause return neutral. |
| Eyes | Independent blink with plausible cadence. | No glowing, hollow or detached eyes. |
| Performance | Responsive desktop/tablet/mobile rendering. | Measure before destructive optimization. |
| Accessibility | Reduced-motion and text-only paths preserve teaching. | 3D remains optional presentation. |
| Evidence | Brave screenshots and test logs represent the actual Meshy runtime. | Record failures and holds; no substituted diagnostic images. |

# Dependencies and hold conditions

No paid model, speech or animation service is authorized.

Hold release if the Meshy face cannot deform cleanly with local rigging.

Hold release if audio, mouth timing, head rotation or stable lighting cannot be demonstrated.

Preserve the current working controller and source GLB before non-destructive rig experiments.

Keep CC BY attribution and synthetic-identity review in the release checklist.