# Weekly Work Plan

27-31 JULY 2026

Reception System  |  Website Form  |  Secure Data Relay  |  Demo  |  Production

# Purpose

Move the locally verified website-to-reception workflow through a controlled hosting, demo and production-readiness process. The week prioritizes visitor-data protection, operational usability, recoverable deployment and evidence-based acceptance.

# Verified starting position

A branded WordPress reception form is implemented at the database-independent /reception/ route.

WordPress validates and rate-limits submissions, then relays them to Laravel using a timestamped HMAC signature and one-use nonce.

WordPress retains no second copy of visitor personal data; the reception application remains authoritative.

Website records enter Reception Control as source=website and status=follow_up with no physical check-in timestamp.

Reception metrics exclude website requests until a staff member records an actual arrival.

An automated local WordPress-to-Laravel request passed and labelled test data was removed; no local browser-review server remains running.

The Laravel suite passes 18 tests and 92 assertions; Pint, PHP syntax, JavaScript syntax and whitespace checks pass.

Independent demo/production roots now exist, but the partially deployed demo returns HTTP 500 until its private environment, database and runtime setup are completed.

# Daily plan

| Day | Primary work | Required output | Release gate |
| --- | --- | --- | --- |
| Mon 27 | Consolidate the integration contract, local evidence, field mapping, privacy boundary, migration and rollback procedure. | Approved technical report, changed-file inventory, passing test record and local database backup. | No remote change; no secrets or PII in Git, reports or browser configuration. |
| Tue 28 | Confirm demo and production reception hostnames, private application paths, public/ document roots, databases, HTTPS, backups and cron capability. | Hosting topology record, access validation and least-privilege deployment checklist. | Do not deploy Laravel into a WordPress public directory or accept invalid TLS. |
| Wed 29 | Resume the partially deployed reception backend: configure a demo-only environment/database, resolve the current HTTP 500, migrate, and verify staff authentication and signed API controls. | Healthy HTTP 200 demo backend, migration evidence, replay rejection, staff register visibility and rollback archive. | Backend health, HTTPS, private-file protection and database backup must pass. |
| Thu 30 | Deploy the reviewed WordPress child-theme files to demo with the form initially disabled; configure the private API URL/secret, enable last, purge cache and test desktop/mobile. | Accepted demo /reception/ page, successful labelled request, staff follow-up record, accessibility and failure-path evidence. | No main-domain work before demo acceptance; remove labelled test records after inspection. |
| Fri 31 | Prepare or execute the main release only after approval. Repeat backups, use a new production secret, deploy backend first, enable the form last and monitor. | Production readiness decision or verified production release, smoke-test record, monitoring snapshot and WMR-13 milestone close. | Named authorization, rollback owner, same-day backups, valid TLS and demo sign-off required. |

# Acceptance criteria

| Area | Completion test | Control |
| --- | --- | --- |
| Public form | Required fields, optional fields, consent, mobile layout, keyboard use and clear success/error states pass. | No sensitive data in URLs, analytics, browser logs or WordPress storage. |
| Signed relay | Valid requests return a WEB reference; stale, changed-signature and replayed requests are rejected. | Different 32+ character secrets for demo and production; server-side storage only. |
| Reception Control | Website request is visible, filterable and editable by authorized staff. | Source remains identifiable and staff access continues to be audited. |
| Attendance integrity | Website follow-ups do not affect check-in totals, QR share or purpose metrics before physical arrival. | Staff transition sets check-in time only when checked-in/checked-out status is selected. |
| Operations | Database backup, migration, scheduler, cache, logs and rollback are verified. | No PII request bodies in logs; encrypted fields and approved retention remain active. |
| Deployment | Demo passes before main; backend is healthy before the website form is enabled. | Fail closed with the reception phone number if the backend or configuration is unavailable. |

# Required owner and hosting inputs

Demo and production reception hostnames.

Private Laravel application directories with document roots mapped only to public/.

Demo and production database credentials, backup method and restore authority.

Certificate-valid HTTPS and a scheduler/cron facility.

Named demo checker, production authorizer and rollback owner.

Privacy/retention confirmation and authorized reception staff accounts.

# Immediate rollback

Set TOOLKIT_RECEPTION_FORM_ENABLED to false and purge LiteSpeed. The public page will retain the phone fallback and stop sending data. Restore the previous child-theme package only for a presentation defect. Roll back Laravel independently; do not reverse the nullable check-in migration while website follow-up records exist. Rotate the shared secret if exposure is suspected.