## Q4 2026 OKRs
ICT & DIGITAL SUPPORT – Q4 2026 OKRs
Individual OKRs – ICT & Digital Support ¦ 1 October–31 December 2026
OBJECTIVE | KEY RESULTS | MILESTONES / ACTIVITIES | TIMELINE
1. Improve Website Accuracy, Admissions and Search Visibility | Keep 100% of published course and fee updates aligned with approved information. | Confirm details with Admissions and Finance; update the website and check the published pages. | Ongoing; monthly review
| Ensure at least 98% of valid demo applications reach the authorised destination during release testing. | Test contact validation, required fields and application handoff on demo; retain results and fix failures. | Each relevant release
| Include 100% of active, approved course pages in the sitemap and relevant website links. | Recheck the search audit findings; correct course discovery and verify sitemap entries and links. | By 30 November
| Complete and verify at least 3 priority mobile performance or usability improvements. | Use the audit and mobile checks to select fixes; compare the same pages before and after each change. | By 30 November
| Complete 3 monthly reviews of website traffic and search visibility. | Confirm first-party analytics data; arrange authorised Search Console access and record available results and gaps. | October, November, December
2. Improve Reception and Staff Reporting Workflows | Complete one signed-in staff acceptance review for Reception and one for Reporting; resolve or assign every finding. | Ask staff to check registration, checkout, record permissions and dashboard links; log results, owners and due dates. | By 31 October
| Review the expanded Reporting modules on a demo or private staging environment and release the approved scope. | Reconcile local and live versions; demonstrate admissions, intake, meetings, reminders and OKRs; deploy after sign-off. | Review by 30 November; approved release by 31 December
| Assign an owner, baseline and evidence source to 100% of adopted Q4 key results. | Confirm accountable staff and measurement rules; enter adopted targets in the OKR register when available. | By 30 November
| Record decisions and next actions for all pending Reception notification, location-checkout and recovery requirements. | Review provider approval, physical boundary tests and backup ownership with the responsible departments. | By 30 November; monthly follow-up
| Complete Wingu field mapping and one non-submitting dry run after the required inputs are approved. | Obtain the attendance-format decision and correction owner; use a human-authenticated session and document the result. | By 31 December, subject to owner inputs
3. Prepare a Governed Virtual Campus and AI Support Pilot | Pass one 20-minute live-class acceptance session on two real devices with a lecturer and learner. | Check audio, video, screen sharing, reconnect and paid/unpaid access on staging; record and address failures. | By 30 November
| Record a pilot go/no-go decision with an owner and next action for every outstanding launch requirement. | Review course and learner data, assessment rules, mail, privacy, capacity and recovery evidence with the Academic lead. | By 31 December
| Ensure 100% of lessons selected for an approved pilot have captions and a low-bandwidth option. | Check selected lesson materials; confirm live-caption arrangements and support guidance before the pilot starts. | Before any pilot launch
| Review at least 20 common questions for Smart Lecturer and the website assistant; all reviewed answers must use approved sources or refer to staff. | Check existing prototypes against current course and policy information; correct unsupported answers and record the review. | By 31 December
4. Strengthen Security, Recovery and Release Reliability | Assign an owner and deadline to every open critical/high audit finding and verify all fixes approved for Q4. | Recheck the hosting and system findings; prioritise access, exposed services and patching; retain evidence or blocker reasons. | Owners by 31 October; fixes by 30 November
| Complete one documented restore exercise each for the website, Reception and Reporting. | Confirm backup owners and restricted locations; restore data and required keys in an isolated environment and record results. | By 31 December
| Complete one access and secret-storage review for every maintained system. | Review privileged accounts, approved staff access and secret-file permissions; remove or correct unauthorised access. | By 30 November
| Ensure 100% of production releases have demo/staging results, a rollback reference and post-release verification. | Use the release checklist; confirm real-page status, asset/release version and runtime errors; record the outcome. | Every release
5. Deliver Consistent Posters and Communications Support | Deliver at least 90% of assigned poster and design requests within the agreed turnaround. | Confirm each brief, required content and deadline; create or revise artwork and track handover and delays. | Continuous; monthly review
| Check and obtain approval for 100% of final artwork before release. | Review branding, readability, dates, contacts and any prices against approved information; retain the approval. | Every handover
| Retain editable sources and required print/digital exports for 100% of completed design requests. | Save approved versions in the shared library with clear names, source files and handover records. | Every handover
| Complete 3 monthly reviews of the communications library. | Update approval status, group repeated copies and archive outdated artwork so current materials are easy to find. | October, November, December
6. Provide Reliable ICT Support and Clear Work Reporting | Acknowledge at least 90% of logged ICT support requests within two working days. | Log staff and desktop issues; give a next action and update unresolved requests until closure or escalation. | Continuous; weekly review
| Record every codebase change in its worklog and provide a daily-report draft for each work session. | Keep evidence and pending work clear; hand the daily draft to the staff member for submission under their own account. | Per change / session
| Complete 3 monthly progress reviews and prepare the Q1 2027 work plan. | Report results against adopted targets, name blocker owners and agree the next quarter priorities with management. | Monthly; Q1 plan by 31 December
Proposed Q4 targets for review. Confirm the individual owner and required approvals; record evidence before reporting completion.

## Basis and Pending Items
ITEM | BASIS / NOTE
Period and status | Q4 2026: 1 October–31 December. Prepared 13 October 2026. These are proposed quarterly targets, not completed results or existing measured performance.
Template and ownership | Uses the shared OKR template.xlsx and its four columns. ICT and Digital Support scope; management should confirm the individual owner and supporting departmental owners.
Website baseline | Recorded October releases cover approved fees, contact validation, testimonial players and an announcement. Search and mobile improvement areas remain in the September audit; recheck findings before acting.
Reception and Reporting baseline | October audit corrections are recorded as deployed. Real-account staff acceptance remains pending. Expanded Reporting modules are locally implemented; the October patch did not deploy those modules.
Campus and AI baseline | Virtual Campus is verified on staging, not approved for production. Human device acceptance and launch inputs remain pending. Smart Lecturer and the website assistant require supervised review; no new public AI release is claimed.
Notification dependencies | Contact-format validation is implemented; ownership verification by email/SMS is not. Approved providers are still needed. Reception WhatsApp delivery and Wingu dispatch are not recorded as operational.
Security and recovery | Read-only September assessments identify open hardening and recovery work. No new security inspection or remediation is claimed by this document.
Continuous poster work | Poster creation and revisions are ongoing assigned work. Targets cover turnaround, approval, source retention and library upkeep; no fixed poster count or named campaign is assumed.
Measurement | For percentages, count successful eligible items divided by all eligible items in the stated period. Report the denominator and evidence. Use N/A when no eligible items exist. Record approvals and missing inputs as blockers; do not count them as completed work.
Evidence used | WordPress WORKLOG.md; October management update and audit report; September ICT monthly report; Report System WORKLOG.md, TODO.md and OWNER_INPUT_TRACKER.md; Reception owner tracker and server inspection; Virtual Campus WORKLOG.md and owner tracker; Chat-bot Git history; SEO/09-BLOCKER-REPORT.md; hardening/HARDENING_AUDIT.md.